## Key
Agile Product backlog keys
| Sprint |  | Priority | Status | Assigned to
| 1 |  | High | Approved | Project Manger
| 2 |  | Medium | In Progress | Environmental Engineer
| 3 |  | Low | Done | Civil Engineer
| 4 |  |  | On Hold | Mechanical Engineer
| 5 |  |  | Need Review | Software Developer
| 6 |  |  |  | Plant operator
| 7 |  |  |  | Maintenance Engineer
| 8 |  |  |  | Compliance officer
Trainer
Support Engineer
Lab Technician
Data analysts
Agile Sprint planning Key
| Feature |  | Assigned to | Priority | Story points |  | Status
| Planning |  | Project Manager | High | 1 |  | Approved
| Analysis |  | Environmental Engineer | Medium | 2 |  | In Progress
| Documentation |  | Civil Engineer | Low | 3 |  | Done
| Construction |  | Mechanical Engineer |  | 5 |  | On Hold
| survey |  | Software Developer |  | 8 |  | Need Review
| Testing |  | Plant operator |  | 13
| compliance |  | Maintenance Engineer
| Quality Assurance |  | Compliance officer |  | 1 | Simple Task
| Communication |  | Trainer |  | 2 | Slightly More Complex Task
| Development |  | Support Engineer |  | 3 | Moderate Task
| Design |  | Lab Technician |  | 5 | complex Task
| Resource management |  | Data analysts |  | 8 | Very Complex Task
| Training |  | Quality Control Specialist |  | 13 | Highly Complex Task
| Preparation |  | Production Team
| Risk management |  | Procurement Team
Procurment
Scheduling
Risk management
Logistics

## Product backlog
Agile Product backlog
User story ID | User story | Priority | Assgined to | Sprint | Status | Estimated Duration (Days)
1 | Conduct the needs assessment of project. | High | Project Manger | 1 | In Progress | 3
2 | Design a water treatment plant. | High | Environmental Engineer | 3 | Done | 10
3 | Conduct installation sites and oversee construction work. | High | Civil Engineer | 2 | In Progress | 180
4 | Conduct the installation of water treatment equipment. | Medium | Mechanical Engineer | 5 | On Hold | 50
5 | Develop and test the prototype of the integrate software. | Medium | Software Developer | 6 | Done | 30
6 | Train the local communities | Low | Trainer | 4 | Approved | 10
7 | Monitor real-time water quality, so that I can ensure safe water distribution. | Low | Plant operator | 8 | In Progress | 3
8 | Generate automated regulatory reports, so that I can ensure legal compliance. | Medium | Compliance officer | 2 | Approved | 5
9 | Access historical test data easily and conduct water quality tests efficiently | Low | Lab Technician | 1 | On Hold | 2
10 | Historical sensor data storage and analysis, so that I can identify trends and optimize processes. | Low | Data Analyst | 7 | In Progress | 5
11 | Track energy usage in real-time, so that I can optimize plant efficiency. | Medium | Project Manger | 8 | In Progress | 2
12 | Receive automated equipment failure alerts, so that I can prevent downtime. | Medium | Maintenance Engineer | 8 | On Hold | 10

## Sprint 1
SPRINT 1
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-03-01 | 2025-03-15 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Schedule site visits | survey | Civil Engineer | 1 | High | 2 | 2025-03-03 | 2025-03-05 | Approved
2 | Assign team members to specific tasks | planning | Project Manager | 1 | High | 1 | 2025-03-04 | 2025-03-05 | Done
3 | Document findings and identify communities | Documentation | Compliance officer | 2 | High | 5 | 2025-03-05 | 2025-03-10 | In Progress
4 | Identify utilities and access points on site | Construction | Civil Engineer | 3 | High | 6 | 2025-03-04 | 2025-03-10 | In Progress
5 | Collect water samples and analyze quality | Testing | Environmental Engineer | 3 | Medium | 2 | 2025-03-10 | 2025-03-12 | In Progress
6 | Assess Existing Infrastructure | Analysis | Civil Engineer | 3 | High | 7 | 2025-03-04 | 2025-03-11 | In Progress
7 | Develop preliminary project plan | Planning | Project Manager | 3 | High | 10 | 2025-03-03 | 2025-03-13 | In Progress
Cost Estimation per sprint
| Cost Component | Estimated Cost (INR) | Percentage of Sprint Cost
| Site Preparation & Civil Work | 8500000 | ~36.3%
| Machinery & Equipment Procurement | 6500000 | ~27.7%
| Labor & Installation Costs | 3000000 | ~12.8%
| Regulatory & Safety Compliance | 1500000 | ~6.4%
| Miscellaneous & Contingencies | 937500 | ~4%
| Salaries (Engineers, Project Managers, Workers, etc.) | 3000000 | ~12.8%
| Total Sprint 1 Cost | 23437500 | 100%

## Sprint2
SPRINT 2
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-03-15 | 2025-03-30 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Analyze the collected water quality data | Analysis | Project manager | 2 | Medium | 2 | 2025-03-17 | 2025-03-19 | Done
2 | Compile assessment report of water quality data | Analysis | Environmental Engineer | 3 | Medium | 4 | 2025-03-16 | 2025-03-20 | In Progress
3 | Share findings stakeholders | Communication | Project Manager | 5 | High | 3 | 2025-03-21 | 2025-03-24 | In Progress
4 | Ensure compliance with safety and environmental regulations | Construction | Civil Engineer | 5 | High | 3 | 2025-03-19 | 2025-03-22 | In Progress
5 | Revise report on stakeholder feedback | communication | Project manager | 3 | Medium | 2 | 2025-03-26 | 2025-03-28 | Done

## Sprint 3
SPRINT 3
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-03-31 | 2025-04-12 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Detailed design specifications | Design | Environmental Engineer | 3 | High | 8 | 2025-03-30 | 2025-04-07 | In Progress
2 | Develop initial prototypes | Development | Software Developer | 8 | High | 7 | 2025-04-01 | 2025-04-08 | In Progress
3 | Review design with stakeholders | communication | Environmental Engineer | 5 | Medium | 3 | 2025-04-04 | 2025-04-07 | In Progress
4 | Prepare design Documentation | Documentation | Environmental Engineer | 3 | Medium | 6 | 2025-04-03 | 2025-04-09 | In Progress
5 | Plan of prototype development | Planning | Project Manager | 5 | High | 2 | 2025-04-02 | 2025-04-04 | In Progress
6 | Feasibility Analysis | Analysis | Environmental Engineer | 3 | Medium | 5 | 2025-03-31 | 2025-04-05 | In Progress
7 | Identify required resources | Resource management | Project Manager | 5 | Medium | 3 | 2025-03-31 | 2025-04-03 | In Progress

## Sprint 4
SPRINT 4
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-04-13 | 2025-04-25 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Implement design changes | Design | Civil Engineer | 8 | High | 12 | 2025-04-13 | 2025-04-25 | In Progress
2 | Finalize design specification | Design | Environmental Engineer | 5 | Medium | 2 | 2025-04-15 | 2025-04-17 | Done
3 | Review the updated design with stakeholders | Communication | Project manager | 3 | High | 4 | 2025-04-14 | 2025-04-18 | Approved
4 | Prepare for development phase | Analysis | Project manager | 8 | Medium | 10 | 2025-04-14 | 2025-04-24 | In Progress
5 | conduct feasibility analysis for Final Design | Analysis | Environmental Engineer | 5 | Medium | 2 | 2025-04-13 | 2025-04-15 | Approved
6 | Identify training needs | Training | Trainer | 2 | Low | 3 | 2025-04-22 | 2025-04-25 | In Progress

## Sprint 5
SPRINT 5
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-04-26 | 2025-05-10 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Prototype development unit | Development | Mechanical Engineer | 3 | High | 2 | 2025-04-27 | 2025-04-29 | Done
2 | Initial functions test of equipment | Testing | Mechanical Engineer | 5 | High | 3 | 2025-04-29 | 2025-05-02 | In Progress
3 | Record the outcomes of functional tests | Documentation | Plant operator | 3 | Medium | 2 | 2025-05-01 | 2025-05-03 | Done
4 | Monitor the Project and prototype | Analysis | Project Manager | 5 | Medium | 3 | 2025-04-30 | 2025-05-03 | In Progress
5 | Refine the prototype based on initial tests | Analysis | Mechanical Engineer | 5 | Low | 4 | 2025-05-03 | 2025-05-07 | In Progress
6 | Prepare prototype for extensive testing | preparation | Mechanical Engineer | 8 | High | 4 | 2025-05-02 | 2025-05-06 | In Progress
7 | Develop testing protocol | planning | Plant operator | 3 | Low | 7 | 2025-05-01 | 2025-05-08 | In Progress

## Sprint 6
SPRINT 6
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-05-10 | 2025-05-21 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Testing of Prototype | Testing | Mechanical Engineer | 3 | High | 2 | 2025-05-12 | 2025-05-14 | Done
2 | Collect feedback from test | Testing | Mechanical Engineer | 2 | Medium | 3 | 2025-05-11 | 2025-05-14 | In Progress
3 | Design adjustment based on feedback | Development | Environmental Engineer | 3 | High | 2 | 2025-05-13 | 2025-05-15 | In Progress
4 | Conduct user acceptance testing | Testing | Plant operator | 5 | Medium | 4 | 2025-05-13 | 2025-05-17 | In Progress
5 | Analyse the performance data during testing | Analysis | Quality Control Specialist | 5 | High | 6 | 2025-05-12 | 2025-05-18 | Done
6 | Prepare detailed test repoerts | Documentation | Quality Control Specialist | 3 | Medium | 7 | 2025-05-13 | 2025-05-20 | Approved
7 | Plan for next testing phase | planning | Project Manager | 3 | Medium | 5 | 2025-05-16 | 2025-05-21 | In Progress

## Sprint 7
SPRINT 7
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-05-21 | 2025-06-05 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Perform Final tests of functionalities work | Testing | Mechanical Engineer | 3 | High | 3 | 2025-05-23 | 2025-05-26 | Approved
2 | Review with stakeholders | Communication | Project Manager | 3 | High | 2 | 2025-05-27 | 2025-05-29 | Done
3 | Secure approval from stakeholders and finalize the prototypes. | Compliance | Compliance officer | 3 | Medium | 3 | 2025-05-26 | 2025-05-29 | Approved
4 | Record and document the outcomes of the final tests. | Documentation | Quality Control Specialist | 2 | Medium | 7 | 2025-05-23 | 2025-05-30 | Approved
5 | Verify Compliance with Standards | Compliance | Compliance officer | 5 | Medium | 6 | 2025-05-28 | 2025-06-03 | Approved
6 | Update all project documentation | Documentation | Project Manager | 3 | High | 7 | 2025-05-29 | 2025-06-05 | In Progress
7 | Plan Transition to Production | Planning | Project Manager | 13 | Medium | 5 | 2025-05-30 | 2025-06-04 | In Progress

## Sprint 8
SPRINT 8
Project name | Safe Water Innovations | Start date | End Date | Overall Progress |  | Project Deliverable | 2025-11-02
Project manger | Nikita Sirse | 2025-06-05 | 2025-06-15 |  |  | Scope Statements
Task Id | Tasks | Feature Type | Assigned to | Story points | Priority | Sprint Duration (Days) | Start Date | End Date | Status
1 | Order Necessary Components and Materials | Procurment | Mechanical Engineer | 2 | High | 2 | 2025-06-06 | 2025-06-08 | In Progress
2 | Plan and schedule production timeline | Scheduling | Project Manager | 5 | High | 4 | 2025-06-06 | 2025-06-10 | In Progress
3 | Arrange logistics and supply chain for transportation | Logistics | Project Manager | 3 | High | 2 | 2025-06-09 | 2025-06-11 | In Progress
4 | Develop detailed Production Plan | Planning | Project Manager | 8 | High | 4 | 2025-06-07 | 2025-06-11 | In Progress
5 | Conduct Supplier Audits | Quality Assurance | Quality Control Specialist | 2 | Medium | 3 | 2025-06-06 | 2025-06-09 | In Progress
6 | Coordinate with Suppliers | Communication | Procurement Team | 3 | Medium | 2 | 2025-06-07 | 2025-06-09 | Done
7 | Prepare Production Facility | Preparation | Production Team | 8 | High | 2 | 2025-06-10 | 2025-06-12 | In Progress
8 | Develop Quality Control Protocols | Quality Assurance | Quality Control Specialist | 5 | Medium | 2 | 2025-06-09 | 2025-06-11 | In Progress
9 | Risk Assessment for Production | Risk Management | Project Manager | 8 | High | 4 | 2025-06-07 | 2025-06-11 | In Progress
10 | Finalize Production Documentation | Documentation | Production Team | 5 | High | 4 | 2025-06-09 | 2025-06-13 | Done

## cost Estimation
COST ESTIMATION
Total Cost for Sprint 8: ₹2,34,37,500
Cost Component | Estimated Cost (INR) | Percentage of Sprint Cost
Final Equipment Installation | 9000000 | ~38.4%
Testing & Quality Assurance | 6500000 | ~27.7%
Final Electrical & Plumbing Work | 3000000 | ~12.8%
Regulatory Compliance Approvals | 1250000 | ~5.3%
Miscellaneous & Contingencies | 687500 | ~2.9%
Salaries (Project Team & Workers) | 3000000 | ~12.8%
Total Sprint 8 Cost | 23437500 | 100%
Total Cost for 4 Months (Sprints 7 & 8): ₹4,68,75,000
Cost Component | Estimated Cost (INR) | Percentage of Total Cost
Infrastructure Finalization | 18000000 | ~38.4%
Technology & Software Integration | 13000000 | ~27.7%
Electrical & Safety Systems | 6000000 | ~12.8%
Regulatory & Legal Approvals | 2500000 | ~5.3%
Miscellaneous & Contingencies | 1375000 | ~2.9%
Salaries (Project Team & Workers) | 6000000 | ~12.8%
Total 4-Month Cost | 46875000 | 100%
Salary Breakdown (For Sprint 8 & 4 Months)
Role | No. of People | Monthly Salary (INR) | Total for Sprint 8 (2 Months) | Total for 4 Months (Sprints 7-8)
Project Manager | 1 | 300000 | 600000 | 1200000
Engineers (Civil, Electrical, Mechanical, etc.) | 5 | ₹1,50,000 each | 1500000 | 3000000
Site Supervisors | 3 | ₹75,000 each | 450000 | 900000
Skilled Workers | 10 | ₹40,000 each | 800000 | 1600000
Total Salaries | - | - | 3000000 | 6000000